## Template
Project Variance Report (Version 1.0)
Budget Variance
|  | Current Budget Variance |  |  |  | Projected Budget Variance at Completion
Project | Report as of Date | Actual Expenditures | Planned Expenditures | Variance Amount | Variance Percentage | Date Baseline Occurred | Baseline Budget | Estimate At Complete | Variance Amount | Variance Percentage | Comments
Project A |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0!
Project B |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0!
Project C |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0!
Project D |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0!
Budget Variance Key
At or under Original or Re-baselined Cost Estimate
Within 0-15% of Original or Re-baselined Cost Estimate
More than 15% of Original or Re-baselined Cost Estimate
Schedule Variance
|  | Current Schedule Variance |  |  |  | Projected Schedule Variance at Completion
Project | Project Start Date | Actual Date | Earned Date | Variance Amount (Days) | Variance Percentage | Date Baseline Occurred | Baseline End Date | Projected End Date | Variance Amount (Days) | Variance Percentage | Comments | Planned | Actual | Planned | Actual
Project A |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  | 0 | 0 | 0 | 0
Project B |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  | 0 | 0 | 0 | 0
Project C |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  | 0 | 0 | 0 | 0
Project D |  |  |  | 0 | #DIV/0! |  |  |  | 0 | #DIV/0! |  | 0 | 0 | 0 | 0
Schedule Variance Key
At or under Original or rebaselined schedule
0-15% of Original or rebaselined schedule
More than 15% of Actual or Baseline Date

## Sample
Project Variance Report (Version 1.0) - SAMPLE
Budget Variance
|  | Current Budget Variance |  |  |  | Projected Budget Variance at Completion
Project | Report as of Date | Actual Expenditures | Planned Expenditures | Variance Amount | Variance Percentage | Date Baseline Occurred | Baseline Budget | Estimate At Complete | Variance Amount | Variance Percentage | Comments
Project A | 2006-08-31 | 1100000 | 1250000 | -150000 | -12% | 2005-05-01 | 1300000 | 1300000 | 0 | 0%
Project B | 2006-08-31 | 1700000 | 1750000 | -50000 | -2.857% | 2005-05-01 | 2400000 | 2300000 | -100000 | -4.167%
Project C | 2006-08-31 | 1300000 | 1250000 | 50000 | 4% | 2006-01-01 | 3150000 | 4000000 | 850000 | 26.98%
Project D | 2006-08-31 | 2000000 | 1800000 | 200000 | 11.11% | 2006-02-01 | 3000000 | 3050000 | 50000 | 1.667%
Budget Variance Key
At or under Original or Re-baselined Cost Estimate
Within 0-15% of Original or Re-baselined Cost Estimate
More than 15% of Original or Re-baselined Cost Estimate
Schedule Variance
|  | Current Schedule Variance |  |  |  | Projected Schedule Variance at Completion
Project | Project Start Date | Actual Date | Earned Date | Variance Amount (Days) | Variance Percentage | Date Baseline Occurred | Baseline End Date | Projected End Date | Variance Amount (Days) | Variance Percentage | Comments | Planned | Actual | Planned | Actual
Project A | 2004-12-01 | 2006-08-31 | 2006-08-31 | 0 | 0% | 2005-03-01 | 2006-08-31 | 2006-11-29 | -90 | 14.11% |  | 638 | 638 | 638 | 728
Project B | 2002-07-17 | 2006-08-31 | 2006-08-31 | 0 | 0% | 2005-12-01 | 2007-01-31 | 2006-12-31 | 31 | -1.869% |  | 1506 | 1506 | 1659 | 1628
Project C | 2003-12-04 | 2006-08-31 | 2006-04-20 | -133 | 15.32% | 2006-03-01 | 2007-07-31 | 2007-10-30 | -91 | 6.816% |  | 1001 | 868 | 1335 | 1426
Project D | 2005-04-08 | 2006-08-31 | 2006-08-01 | -30 | 6.25% | 2006-07-01 | 2007-02-15 | 2007-06-26 | -131 | 19.32% |  | 510 | 480 | 678 | 809
Schedule Variance Key
At or under Original or rebaselined schedule
0-15% of Original or rebaselined schedule
More than 15% of Actual or Baseline Date