## CPM
| Start Date |  |  |  | Days to Completion
| 2017-01-01 |  |  |  | 20
Finish Date
#REF!
Times (in Days)
[5 empty] | Time Distribution: | Triangular | [5 empty] | [42] | [24 empty] | Series Used in the Gantt Chart | [7 empty] | Weeks | Days
ID | Task Name | Predecessors (Enter one ID per cell) |  | O (min) | M (most likely) | P (max) | Duration (exp. time) | ES | EF | LS | LF | Slack | EF of Predecessors | [5 empty] | Successors | [8 empty] | LS of Successors | [8 empty] | ES | Critical | +T | -T | Duration | +T | -T | Slack | Events | Events | Axis
10 | Start | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | 30 | [7 empty] | 0 | 3.6667 | [6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
20 | Task A | 10 |  | 2 | 4 | 6 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 40 | 50 | [7 empty] | 4 | 8.3333 |  |  |  |  | 0 | 4 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 0.5
30 | Task B | 10 |  | 3 | 5 | 9 | 5.6667 | 0 | 5.6667 | 3.6667 | 9.3333 | 3.6667 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 60 | [8 empty] | 9.3333 |  |  |  | 0 | #N/A | #N/A | #N/A | 5.6667 | 3.3333 | 2.6667 | 3.6667 | #N/A | #N/A | 1.5
40 | Task C | 20 |  | 4 | 5 | 7 | 5.3333 | 4 | 9.3333 | 4 | 9.3333 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 60 | [8 empty] | 9.3333 |  |  |  | 4 | 5.3333 | 1.6667 | 1.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 2.5
50 | Task D | 20 |  | 4 | 6 | 10 | 6.6667 | 4 | 10.6667 | 8.3333 | 15 | 4.3333 | 4 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 70 | [8 empty] | 15 |  |  | 4 | #N/A | #N/A | #N/A | 6.6667 | 3.3333 | 2.6667 | 4.3333 | #N/A | #N/A | 3.5
60 | Task E | 30 | 40 | 4 | 5 | 7 | 5.3333 | 9.3333 | 14.6667 | 9.3333 | 14.6667 | 0 | 5.6667 | 9.3333 | 0 | 0 | 0 | 0 | [7 empty] | 80 | [8 empty] | 14.6667 |  | 9.3333 | 5.3333 | 1.6667 | 1.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 4.5
70 | Task F | 50 |  | 3 | 4 | 8 | 5 | 10.6667 | 15.6667 | 15 | 20 | 4.3333 | 10.6667 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 90 | [8 empty] | 20 | 10.6667 | #N/A | #N/A | #N/A | 5 | 3 | 2 | 4.3333 | #N/A | #N/A | 5.5
80 | Task G | 60 |  | 3 | 5 | 8 | 5.3333 | 14.6667 | 20 | 14.6667 | 20 | 0 | 14.6667 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 90 | [8 empty] | 20 | 14.6667 | 5.3333 | 2.6667 | 2.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 6.5
90 | Finish | 70 | 80 |  |  |  | 0 | 20 | 20 | 20 | 20 | 0 | 15.6667 | 20 | 0 | 0 | 0 | 0 | [18 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4 | 20 | 7.5
Note on B5: Finish Date: The Finish Date uses the WORKDAY() function to calculate the date to completion, excluding weekends and the holidays listed in the Holidays worksheet. If you see a #NAME or other error in the Finish Date, you probably need to install the Analysis ToolPak and then recalculate the worksheet by pressing Ctrl+Alt+F9.
Note on A9: Task ID: Normally, you would start by assigning IDs as 10, 20, 30, etc. However, the ID can be anything you want, including text.
Note on B9: Task Name: The task name is a description that will show up in the gantt chart. The task name will be bolded if the task is a critical task. This is done through conditional formatting.
Note on C9: Predecessors: The set of events immediately preceding the task. In a network diagram or PERT chart, the predecessors for a particular task are all the tasks which have arrows pointing to that particular task. - Each predecessor needs to refer to the ID in column A. Successors: The set of events immediately following a particular task. In a network diagram or PERT chart, arrows are drawn from a task to its successors.
Note on I9: Optimistic Time (O): The minimum time required to complete the task. Assumes that everything proceeds faster than normal.
Note on J9: Most Likely Time (M): The most likely time required to complete the task, assuming everything proceeds as normal.
Note on K9: Pessimistic Time (P): The maximum time required to complete the task. Assumes that everything proceeds slower than normal.
Note on L9: Duration or Expected Time: Using a Beta distribution, where O is the minimum, P is the maximum, and M is the most likely value, the formula for calculating the mean or expected time is: Duration = (O+4M+P)/6 Using a Triangular distribution, the mean of the distribution would be: Duration = (O+M+P)/3
Note on M9: Early Start Time: The ES is the maximum EF of all predecessors, except for the first task where the ES=0.
Note on N9: Early Finish Time: The EF time is the ES time plus the duration (EF=ES+Duration).
Note on O9: Late Start Time: The LS time is calculated as the LF time minus the duration (LS=LF-Duration).
Note on P9: Late Finish Time: The LF time is the minimum LS of all the successors, except for the last task where LF equals EF.
Note on Q9: Slack Time: The Slack time is calculated as LF minus EF. It can also be calculated as LS minus ES. If the slack is zero, then the task is on the critical path.

## ©
Critical Path Method
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2010-2020 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.