## Excel Critical Path Tracker
Critical Path Tracker | [10 empty] | - Critical Path |  |  |  |  | - Non Critical Path |  |  |  |  | DIDx - Predecessors' ID | [9 empty] | 0
[15 empty] | x | - Holiday
PROJECT START DATE |  | 2019-09-01 |  | TODAY DATE | TODAY DATE | 2019-09-07
[8 empty] | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18
ID* | Items* | Task Duration | DID1* | Start Date | Helper | Finish Date | PERIODS | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23
1 | Task 1 | 2 |  | 2019-09-01 | 2019-09-01 | 2019-09-03 | bar: 2019-09-02 to 2019-09-03
2 | Task 2 | 1 | 1 |  | 2019-09-04 | 2019-09-05
3 | Task 3 | 3 | 2 |  | 2019-09-06 | 2019-09-11
4 | Task 4 | 3 | 3 |  | 2019-09-12 | 2019-09-17
5 | Task 5 | 4 |  | 2019-09-12 | 2019-09-12 | 2019-09-18
6 | Task 6 | 1 | 5 |  | 2019-09-19 | 2019-09-20
7 | Task 7 | 2 | 5 |  | 2019-09-19 | 2019-09-23
8 | Task 8 | 6 |  | 2019-09-04 | 2019-09-04 | 2019-09-12
9 | Task 9 | 2 | 8 |  | 2019-09-13 | 2019-09-17
10 | Task 10 | 1 | 5 |  | 2019-09-19 | 2019-09-20
C
C
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of
PowerPoint. Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce a PowerPoint Gantt chart slide.
Note on G9: If highlighted, enter date

## Holidays
Critical Path Tracker
Holiday every |  | Y/N*
| Sunday | Y
| Monday | N
| Tuesday | N
| Wednesday | N
| Thursday | N
| Friday | N
| Saturday | Y
Holiday on |  | Date (maximum of 40 dates)*
|  | 2009-12-25 | Christmas Day | 2009-12-25
|  | 2010-01-01 | New Year's Day | 2016-01-01
|  | 2010-01-18 | Martin Luther King Day | 2016-01-18
|  | 2010-02-15 | Presidents Day | 2016-02-15
|  | 2010-05-31 | Memorial Day | 2016-05-31
|  | 2010-07-04 | Independence Day | 2016-07-04
|  | 2010-09-06 | Labor Day | 2016-09-06
|  | 2010-10-11 | Columbus Day | 2016-10-11
|  | 2010-11-11 | Veterans' Day | 2016-11-11
|  | 2010-11-25 | Thanksgiving Day | 2016-11-25
|  | 2010-12-25 | Christmas Day